## Weekly_Review
week_starting | notable_outputs | blockers | klarna_test_status | kpi_movements | decisions_due | meeting_notes | brain_link
2026-04-13 | [SAMPLE] Davor S-tier onboarding rebuild merged; Anya signed Acme MSA; Mira payment-rail PR. | [SAMPLE] Anya: Acme legal review (ETA 2026-04-22). Mira: Stripe deprecation. | [SAMPLE] KT-2026-014 proceeded (16/20). KT-2026-015 in scoring. | [SAMPLE] Customer count 84→87. Runway 18.2→17.9 months. ai_skill_roi 4.2→4.6. | [SAMPLE] D-2026-04-007 Unit Fund pilot Q3; D-2026-04-009 Stripe→Adyen. | (filled during meeting) | [[business-reviews/2026-04-17]]

## Monthly_BR
month | total_outputs | total_variable_paid | gross_margin | treasury_runway_months | customer_count_delta | partner_count | klarna_tests_proceeded | klarna_tests_held | ai_skill_roi
[SAMPLE]2026-03 | 47 | 28500 | 0.62 | 18.2 | 3 | 8 | 1 | 0 | 4.2

## Decisions_Log
decision_id | date | decision | accountable | consulted | brain_link | reversal_threshold | review_date
D-2026-04-007 | 2026-04-17 | [SAMPLE] Defer Unit Fund pilot until counsel sign-off. | founder-tali | davor,anya,mira | [[decisions/D-2026-04-007]] | If counsel signs off before 2026-06-15, revisit at next BR. | 2026-06-15

## Blockers
blocker_id | raised_date | description | partner_blocked | owner | status | resolved_date | brain_link
[SAMPLE]B-2026-04-001 | 2026-04-15 | Acme legal review of long-tail clause | anya-gorska | anya-gorska | open |  | [[blockers/2026-04-15-acme-legal]]

## Klarna_Test_Hits
test_id | summary | status | score | decision | review_date_90d
[SAMPLE]KT-2026-014 | Replace manual customer-onboarding email with AI drafter | proceeded | 16 | PROCEED | 2026-08-12

## _metadata (hidden)
key | value
spec_version | 1.0.0
generation_date | 2026-07-04
oot_version | 1.0.0
file_id | X3

## README
# business-review.xlsx
PURPOSE
Friday Business Review working document. Generated by Routine R2; reviewed in the BR; outcomes committed to the Brain.
WRITTEN BY
- Routine R2 (Weekly BR Prep, Friday 08:00) — populates Weekly_Review row.
- Scribe during/after the meeting — fills meeting_notes; appends decisions_log entries; updates blockers.
READ BY
- BR participants pre-meeting (Friday 09:00 onwards).
- Skill Pack S5 (Reporting & Business Review) at all times.
DO NOT
- Skip the Klarna status block even if no open tests exist.
- Auto-publish BR summaries externally — they may contain sensitive partner-level data.
- Take a decision in the BR without creating a corresponding firm/decisions/D-YYYY-NNN.md page during the meeting.